## Tasks
Tasks | Due Date | Owner
Learn gem5 | 2019-03-29 | Everyone
Combine multiple sets into partitions | 2019-03-29 | Ranjan
At every cache access, calculate total of priority values in each partition and update all necessary registers (GTRs, preGTRs, PTRs , prePTRs) | 2019-03-29 | Vatsal
At every set interval, check fluctuations of the total of priority values in all partitions and then switch policies | 2019-03-29 | Piyush
Define Policies - Insertion Policy, Promotion Policy, Demotion Policy, Selection Policy | 2019-04-08 | Everyone
Merging | 2019-04-11 | Everyone
Test | 2019-04-11 | Piyush, Vatsal
Benchmarking, Performance Evaluation | 2019-04-17 | Rohan, Ranjan
Presentation | 2019-04-21 | Everyone
Project Report | 2019-04-30 | Everyone

## Responsibilities
Ranjan Raut :- Ranjan was involved in research for tool and module for implementation and Identified the way to implement policy in adherence to the framework of simulator. He also implemented code for Combining multiple sets into partitions, Insertion Policy and was also involved in performance evaluation of policy. He also contributed into preparing presentations for research and project. Ranjan reviewed complete code for the project just to ensure the functionality if implemented correctly.
Rohan Hulsure :- Rohan was responsible for implementation of module of switching policies and implementation of promotion policy. He also identified the way gem5 can be integrated with SPEC CPU2017 benchmark, compiled libraries of SPEC CPU2017 and prepared script for gem5 by which policy can be evaluated. He also has contribution in preparing presentations for research and project. Rohan made sure that each task was completed at regular checkpoints.
Vatsal Vador :- Vatsal also was involved in research for tool and module for implementation. Vatsal was responsible for implementation for the logic for task ‘At every cache access, calculate total of priority values in each partition and update all necessary priority values (GTRs, preGTRs, PTRs , prePTRs) and implementation of Demotion Policy. He also had contribution in documentation of project work (Project Report). Vatsal had on more responsibility of testing each module of the project.
Piyush Deshpande :- Piyush was responsible for the implementation of logic for the task ‘At every set interval, check fluctuations of the total of priority values in all partitions and then switch policies’ and implementation for Selection Policy. He also had contribution in documentation of project work (Project Report), testing end to end functionality and code optimization for complete project.