## Tasks
Tasks | Due Date | Owner
Learn gem5 | 2019-03-29 | Everyone
Combine multiple sets into partitions | 2019-03-29 | Ranjan
At every cache access, calculate total of priority values in each partition and update all necessary registers (GTRs, preGTRs, PTRs , prePTRs) | 2019-03-29 | Vatsal
At every set interval, check fluctuations of the total of priority values in all partitions and then switch policies | 2019-03-29 | Piyush
Define Policies - Insertion Policy, Promotion Policy, Demotion Policy, Selection Policy | 2019-04-08 | Everyone
Merging | 2019-04-11 | Everyone
Test | 2019-04-11 | Piyush, Vatsal
Benchmarking, Performance Evaluation | 2019-04-17 | Rohan, Ranjan
Presentation | 2019-04-21 | Everyone
Project Report | 2019-04-30 | Everyone